## Schedule
| Group Schedule | Week's activity | Scrum Activity | Deliverables uploaded to file exchange
Sprint 1 | Week 7 | Define marking criteria; Gather all the group info (email & phones) define schedule and sprints; Start to look at the case study and come up with entities; | Sprint 1 planning | Draft of the entities to File Exchange, backlog draft, schedule draft
| Week 8 | Discuss the ER diagram | Meeting 1: "daily stand up"; Meeting 2: Planning Sprint 2 | ER diagram; backlog, schedule
Sprint 2 | Week 9 | Identify Functional Requirements, Finalising ER diagram, normalisation and Entity Specs | Meeting: SPRINT 1 REVIEW and RETROSPECTIVE Sprint 2 planning | Individual tasks
| Week 10 | Tables creation | SPRINT 2 ‘Daily stand up’ | Backlog, schedule
Sprint 3 | Week 11 | Table creation and test data | Sprint 3 planning, ‘daily stand up | Individual tasks
| Week 12 | Implementing 8 queries | SPRINT 3 REVIEW and RETROSPECTIVE Sprint 4 planning | Backlog, schedule
Sprint 4 | Week 13 | Security and other systems | ‘Daily stand up’ | Individual tasks
| Week 14 | Security and other systems Tidying up documentation | ‘daily stand up’ REVIEW and RETROSPECTIVE | Backlog, schedule; Final report and peer assessment submitted.