## Sheet1
Task No. | Description | Allocated to team member | Meeting duration(min) | Due Date | Date Posted to Exchange | Status | Re-allocated to? | New Due Date | Notes
| Post hello message to group members on group blog or whatsapp group | Mohammed Suleman | N/A | 2023-03-30 | N/A | N/A | N/A | N/A | Scrum Master: Angela until 17/04/2023
| as above | Gabriel | N/A | as above | N/A | N/A | N/A | N/A
| as above | Sarah | N/A | as above | N/A | N/A | N/A | N/A
| as above | Toufeeq | N/A | as above | N/A | N/A | N/A | N/A
| as above | Federico | N/A | as above | N/A | N/A | N/A | N/A
| as above | Angela | N/A | as above | N/A | N/A | N/A | N/A
| First face-to-face meeting(Topic: Introduction to the team, Sprint 1 planning, Peer marking critiria discussion) | Mohammed Suleman | 60 | as above | N/A | N/A | N/A | N/A
| as above | Gabriel | N/A | as above | N/A | N/A | N/A | N/A
| as above | Sarah | N/A | as above | N/A | N/A | N/A | N/A
| as above | Toufeeq | N/A | as above | N/A | N/A | N/A | N/A
| as above | Federico | N/A | as above | N/A | N/A | N/A | N/A
| as above | Angela | N/A | as above | N/A | N/A | N/A | N/A
| Post Peer Marking Criteria on Group Blog | Gabriel | N/A | 2023-03-30 | 2023-03-30 | Completed | N/A | N/A
| Post draft of Draft Product Blog | Angela | N/A | 2023-03-30 | 2023-03-30 | Completed | N/A | N/A
| Post Group schedule on Blog | Sarah | N/A | 2023-03-30 | 2023-03-30 | Completed | N/A | N/A
SPRINT 1
| Create and Post the first ER diagram on Group blog/ File exchange | Mohammed Suleman | N/A | 2023-04-04 | 2023-04-02 | Completed | N/A | N/A
| as above | Gabriel | N/A | as above | 2023-04-02 | as above | N/A | N/A
| as above | Sarah | N/A | as above | 2023-04-01 | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | 2023-04-02 | as above | N/A | N/A
| as above | Federico | N/A | as above | 2023-03-31 | as above | N/A | N/A
| as above | Angela | N/A | as above | 2023-03-31 | as above | N/A | N/A
| Second face-to-face meeting(Topic: Brainstorming and discussion on ER diagram proposed) | Mohammed Suleman | 60 | 2023-04-04 | 2023-04-04 | Completed | N/A | N/A
| as above | Gabriel | N/A | as above | as above | as above | N/A | N/A
| as above | Sarah | N/A | as above | as above | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | as above | as above | N/A | N/A
| as above | Federico | N/A | as above | as above | as above | N/A | N/A
| as above | Angela | N/A | as above | as above | as above | N/A | N/A
| Defining Entities Relationships, Attributes | Mohammed Suleman | N/A | 2023-04-06 | 2023-04-06 | Completed | N/A | N/A
| as above | Gabriel | N/A | as above | 2023-04-02 | as above | N/A | N/A
| as above | Sarah | N/A | as above | 2023-04-04 | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | 2023-04-02 | as above | N/A | N/A
| as above | Federico | N/A | as above | 2023-03-31 | as above | N/A | N/A
| as above | Angela | N/A | as above | 2023-04-02 | as above | N/A | N/A
| Third-Face-To-Face Meeting(Topic: Brainstorming and discussion on Entities, attributes and relations) | Mohammed Suleman | 60 | 2023-04-06 | 2023-04-06 | Completed | N/A | N/A
| as above | Gabriel | N/A | as above | as above | as above | N/A | N/A
| as above | Sarah | N/A | as above | as above | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | as above | as above | N/A | N/A
| as above | Federico | N/A | as above | as above | as above | N/A | N/A
| as above | Angela | N/A | as above | as above | as above | N/A | N/A
| Review the ER and post on group if agree with it | Mohammed Suleman | N/A | 2023-04-08 | 2023-04-08 | Completed | N/A | N/A
| as above | Gabriel | N/A | as above | as above | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | as above | as above | N/A | N/A
| as above | Federico | N/A | as above | as above | as above | N/A | N/A
| as above | Angela | N/A | as above | as above | as above | N/A | N/A
| Upload Final Version of ER Diagram | Sarah | N/A | 2023-04-10 | 2023-04-10 | Completed | N/A | N/A
| Come up with 8 functional requirments | Mohammed Suleman | N/A | 2023-04-12 | 2023-04-12 | Completed | N/A | N/A
| as above | Gabriel | N/A | as above | 2023-04-02 | as above | N/A | N/A
| as above | Sarah | N/A | as above | 2023-04-06 | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | 2023-04-13 | as above | N/A | N/A
| as above | Federico | N/A | as above | 2023-04-11 | as above | N/A | N/A
| as above | Angela | N/A | as above | 2023-04-11 | as above | N/A | N/A
| Meeting on Blackboard to Discuss Functional Requirements. Everyone to bring 8 Functional Requirements. | Mohammed Suleman | 120 | 2023-04-13 | Re-allocated | Re-allocated | N/A | 2023-04-17
| as above | Gabriel | N/A | as above | 2023-04-13 | Completed | N/A | N/A
| as above | Sarah | N/A | as above | as above | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | as above | as above | N/A | N/A
| as above | Federico | N/A | as above | as above | as above | N/A | N/A
| as above | Angela | N/A | as above | as above | as above | N/A | N/A
| Functional requirement post | Mohammed Suleman | N/A | 2023-04-17 | 2023-04-12 | as above | N/A | N/A
| SPRINT 1 Backlog | Angela |  | N/A | 2023-03-30 | Completed | N/A | N/A | shared mainly on shared OneDrive
SPRINT 2
| Fourth-Face-To-Face Meeting (Topic: Entity individual assignment for Normalization, Entity specs individual assignment, retrospective, Sprint 2 planning) | Mohammed Suleman | 60 | 2023-04-18 | 2023-04-18 | Completed | N/A | N/A | Scrum Master: Federico until 30/04/2023
| as above | Gabriel | N/A | as above | as above | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | as above | as above | N/A | N/A
| as above | Federico | N/A | as above | as above | as above | N/A | N/A
| as above | Angela | N/A | as above | as above | as above | N/A | N/A
| as above | Sarah | N/A | as above | as above | as above | N/A | N/A
| Upload individual Normalised entities | Mohammed Suleman | N/A | 2023-04-20 | 2023-04-20 | Completed | N/A | N/A
| as above | Gabriel | N/A | as above | as above | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | as above | as above | N/A | N/A
| as above | Federico | N/A | as above | as above | as above | N/A | N/A
| as above | Angela | N/A | as above | as above | as above | N/A | N/A
| as above | Sarah | N/A | as above | as above | as above | N/A | N/A
| Fifth-Face-To-Face Meeting (Topic: Definition of normalised entities, Entity specs individual assignment) | Mohammed Suleman | 80 | 2023-04-20 | 2023-04-20 | Absent | N/A | N/A | Authorized Absence
| as above | Gabriel | N/A | as above | 2023-04-20 | Completed | N/A | N/A
| as above | Toufeeq | N/A | as above | 2023-04-20 | as above | N/A | N/A
| as above | Federico | N/A | as above | 2023-04-19 | as above | N/A | N/A
| as above | Angela | N/A | as above | 2023-04-19 | as above | N/A | N/A
| as above | Sarah | N/A | as above | 2023-04-19 | as above | N/A | N/A
| Upload individual entity specs | Mohammed Suleman | N/A | 2023-04-27 | 2023-04-27 | Re-allocated | N/A | 2023-04-29
| as above | Gabriel | N/A | as above | 2023-04-26 | Completed | N/A | N/A
| as above | Toufeeq | N/A | as above | 2023-04-26 | as above | N/A | N/A
| as above | Federico | N/A | as above | 2023-04-25 | as above | N/A | N/A
| as above | Angela | N/A | as above | 2023-04-26 | as above | N/A | N/A
| as above | Sarah | N/A | as above | 2023-04-27 | as above | N/A | N/A
| Specs post upload | Mohammed Suleman | N/A | 2023-04-29 | 2023-04-29 | as above | N/A | N/A
| Sixed-Face-To-Face Meeting (Topic: Table specs finalization and discussion, Sprint 3 planning ) | Mohammed Suleman | 180 | 2023-04-27 | 2023-04-27 | Completed | N/A | N/A
| as above | Gabriel | N/A | as above | as above | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | as above | as above | N/A | N/A
| as above | Federico | N/A | as above | as above | as above | N/A | N/A
| as above | Angela | N/A | as above | as above | as above | N/A | N/A
| as above | Sarah | N/A | as above | as above | as above | N/A | N/A
| Upload individual table creation script as Group blog assignment | Mohammed Suleman | N/A | 2023-05-03 | 2023-05-03 | Completed | Gabriel | 2023-05-05
| as above | Gabriel | N/A | 2023-05-03 | as above | as above | N/A | N/A
| as above | Toufeeq | N/A | 2023-05-04 | as above | as above | N/A | N/A
| as above | Federico | N/A | 2023-05-03 | as above | as above | N/A | N/A
| as above | Angela | N/A | 2023-05-03 | as above | as above | N/A | N/A
| as above | Sarah | N/A | 2023-05-04 | as above | as above | N/A | N/A
| Entity script upload | Mohammed Suleman | N/A | 2023-05-05 | 2023-05-04 | as above | N/A | N/A
| SPRINT 2 Backlog | Federico |  | N/A | 2023-04-27 | Completed | N/A | N/A
| SPRINT 3 - Gabriel Scrum Master from 01/05/2023 until 15/05/2023 | [7 empty] | Scrum Master: Gabriel until 15/05/2023
| 7th-Face-To-Face Meeting (Topic: Upload Individual Table Creation Scripts + various updates) | Mohammed Suleman | 180 | 2023-05-04 | 2023-05-04 | Completed | N/A | N/A
| as above | Gabriel | N/A | as above | as above | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | as above | as above | N/A | N/A
| as above | Federico | N/A | as above | as above | as above | N/A | N/A
| as above | Angela | N/A | as above | as above | as above | N/A | N/A
| as above | Sarah | N/A | as above | as above | as above | N/A | N/A
| Post - all table creation scripts in order tested version 1 (individual work) + as above | Sarah | N/A | 2023-05-06 | 2023-05-06 | Completed | N/A | N/A
| Post - all table creation scripts in order tested version 2 (individual work) + as above | Sarah | N/A | 2023-05-08 | 2023-05-08 | Completed | N/A | N/A
| 8th-Face-To-Face Meeting (Topic: Upload Individual Sample Data Insertion Scripts + various updates) | Mohammed Suleman | 180 | 2023-05-11 | 2023-05-11 | Completed | N/A | N/A
| as above | Gabriel | N/A | as above | as above | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | as above | as above | N/A | N/A
| as above | Sarah | N/A | as above | as above | as above | N/A | N/A
| as above | Federico | N/A | as above | as above | as above | N/A | N/A
| as above | Angela | N/A | as above | as above | as above | N/A | N/A
| as above | Sarah | N/A | as above | as above | as above | N/A | N/A
| Running table creation scripts and data insertion scripts (Sarah Leading) + as above | Sarah | N/A | as above | as above | as above | N/A | N/A
| Post - Functional Requirements assigned per member for creating queries + as above | Angela | N/A | as above | as above | as above | N/A | N/A
| Creating sequence pattern for the IDs - Individual work + as above | Angela | N/A | 2023-05-12 | 2023-05-12 | Completed | N/A | N/A
| Extension for providing data insertion scripts | Mohammed Suleman | N/A | as above | 2023-05-13 | Re-allocated | 2023-05-15 | Sarah
| SPRINT 3 Backlog | Gabriel |  | N/A | 2023-05-15 | Completed | N/A | N/A
| SPRINT 4 - Toufeeq - taking over as Scrum Master | [7 empty] | Scrum Master: Toufeeq until 29/05/2023
| 9th-Face-To-Face Meeting (Topic: Upload Individual Queries) | Mohammed Suleman | 180 | 2023-05-16 | 2023-05-16 | Completed | N/A | N/A
| as above | Gabriel | N/A | as above | as above | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | as above | as above | N/A | N/A
| as above | Federico | N/A | as above | as above | as above | N/A | N/A
| as above | Angela | N/A | as above | as above | as above | N/A | N/A
| as above | Sarah | N/A | as above | as above | as above | N/A | N/A
| 9th-Face-To-Face Meeting(Topic: Confirmation of queries and security implementation) | Mohammed Suleman | 180 | 2023-05-18 | 2023-05-18 | Completed | N/A | N/A
| as above | Gabriel | N/A | as above | as above | as above | N/A | N/A
| as above | Toufeeq | N/A | as above | as above | as above | N/A | N/A
| as above | Angela | N/A | as above | as above | as above | N/A | N/A
| as above | Sarah | N/A | as above | as above | as above | N/A | N/A
| as above | Federico | N/A | as above | as above | as above | N/A | N/A
| Post assigned implements queries | Mohammed Suleman | N/A | 2023-05-16 | 2023-05-16 | ongoing | N/A | 2023-05-18
| as above | Gabriel | N/A | as above | 2023-05-15 | Completed | N/A | N/A
| as above | Toufeeq | N/A | as above | 2023-05-14 | ongoing | Sarah | 2023-05-16
| as above | Federico | N/A | as above | 2023-05-12 | Completed | N/A | N/A
| as above | Angela | N/A | as above | 2023-05-12 | Completed | N/A | N/A
| as above | Sarah | N/A | as above | 2023-05-14 | Completed | N/A | N/A
| Toufeeq query implementation | Sarah | N/A | 2023-05-16 | 2023-05-16 | Completed | N/A | N/A
| Final script Creation and Management on Oracle group account | Sarah | N/A | 2023-05-24 | 2023-05-24 | Completed | N/A | N/A
| Report Generation and No SQL research and final backlog | Federico | N/A | as above | 2023-05-21 | as above | N/A | N/A
| Making ER (Entity-Relationship) Diagrams | Gabriel | N/A | as above | 2023-05-20 | as above | N/A | N/A
| Security Research and No SQL database research | Mohammed Suleman | N/A | as above | 2023-05-25 | as above | N/A | N/A
| Security research and indexes creation | Angela | N/A | as above | 2023-05-24 | To update | N/A | 2023-05-26
| No SQL research | Toufeeq | N/A | 2023-05-25 | 2023-05-24 | as above | N/A | N/A
| Updating Data in Scrum Files- creating up to date final specs | Toufeeq | N/A | 2023-05-19 | 2023-05-19 | as above | N/A | N/A
| 10th-Face-To-Face Meeting (Topic: Review Project Progress and Plan for Final Deliverables) | Mohammed Suleman | 180 | 2023-05-25 | 2023-05-25 | Completed | N/A | N/A
| as above | Gabriel | as above | as above | as above | as above | N/A | N/A
| as above | Toufeeq | as above | as above | as above | as above | N/A | N/A
| as above | Federico | as above | as above | as above | as above | N/A | N/A
| as above | Angela | as above | as above | as above | as above | N/A | N/A
| as above | Sarah | as above | as above | as above | as above | N/A | N/A
| Upload all scripts in the Oracle group account and update all script | Sarah | N/A | 2023-05-25 | N/A | N/A | N/A | N/A
| Security mesures implementation script | Angela | N/A | 2023-05-26 | 2023-05-26 | Completed | N/A | N/A
| SPRINT 4 Backlog | Toufeeq |  | N/A | 2023-05-20 | Completed | N/A | N/A
| Post final report and backlog generation | Federico | N/A | 2023-05-26 | 2023-05-26 | Completed | N/A | N/A